## 3-Week Look-Ahead
3-Week Look-Ahead Schedule
Enter your Week 1 start date, then log each activity below. Update the three status columns as the week progresses.
Week 1 Start Date (Monday) |  | 2026-08-03
Total Activities |  |  |  | Critical Path (Open) |  |  |  | Weather-Sensitive (Open) |  | Delayed (Any Week)
3 |  |  |  | 1 |  |  |  | 0 |  | 0
Activity / Task | Trade / Sub | Location / Area | Predecessor / Dependency | Week 1 | Week 2 | Week 3 | Critical Path? (Y/N) | Weather-Sensitive? (Y/N) | Notes / Constraints
|  |  |  | Aug 3 - Aug 9 | Aug 10 - Aug 16 | Aug 17 - Aug 23
Form and pour Level 1 retaining wall footings, Grid A-C | Concrete Sub | Site - West Wall | Excavation complete | Complete | Complete | N/A | Y | Y | Weather hold used 2 days in Week 1; recovered by Friday.
Set structural steel, Level 2, Grid A-D | Steel Sub | Level 2 | Level 1 concrete cure (SUB-021 approval) | In Progress | In Progress | Not Started | Y | N | Tracking against RFI-017 connection detail confirmation.
Rough-in electrical, Suite 210 | Electrical Sub | Level 2, Suite 210 | Framing inspection sign-off | Not Started | In Progress | In Progress | N | N | Waiting on panel schedule clarification (RFI-020).

## README
3-Week Look-Ahead Schedule — Template
Free field tool for PEs, Coordinators, and PMs — part of FieldToolsKit.com
WHAT THIS IS
A rolling three-week schedule for tracking planned activities by trade, flagging critical-path and weather-sensitive work, and catching what's falling behind before it compounds. This is a weekly-bucket format (three status columns), not a day-by-day bar chart — built this way deliberately so it stays easy to update in five minutes each week instead of becoming a chore.
DOES THIS REPLACE PRIMAVERA P6?
No. P6 (or your firm's scheduling software) should still run the master CPM schedule — that's the schedule of record. This tool fills a different, well-known gap: P6 updates on a slower cycle and isn't something supers and subs open daily, so field-level weekly look-aheads are very commonly still kept as a simple working document like this one, even at firms running P6.
HOW TO USE IT
1. Enter the Monday date for Week 1 in the yellow 'Week 1 Start Date' cell. Weeks 2 and 3 date ranges calculate automatically from that one entry.
2. Add one row per activity. Only yellow cells need your input.
3. Update each week's status column as the week progresses: Not Started, In Progress, Complete, or Delayed. Use the dropdown.
4. Mark Critical Path and Weather-Sensitive with Y or N so the summary counts stay accurate.
5. Each Monday, shift your attention: last week's Week 1 column becomes historical, Week 2 becomes the new Week 1 focus, and you add a new Week 3 further out. This template doesn't auto-shift columns — re-enter the Week 1 Start Date each week and the date labels update.
HOW THE FORMULAS WORK
Week date ranges: Week 1 = your entered start date through +6 days. Week 2 = +7 through +13. Week 3 = +14 through +20. All three labels recalculate from the single Week 1 Start Date cell.
Summary cards: Critical Path Count and Weather-Sensitive Open Count both count only rows flagged Y where Week 3 status is not 'Complete' and not 'N/A' — so items finished earlier in the window, or not applicable to Week 3, drop off the count automatically. Delayed Count checks all three week columns for any 'Delayed' status.
COLOR KEY
Yellow fill = editable input cells.
Status columns: grey = not started, yellow = in progress, green = complete, red = delayed.
This is a free tool, not a substitute for your project's CPM schedule. Use it as the weekly field-level companion to that schedule, not a replacement for it.