## Closeout Checklist
Project Closeout Checklist
Update Status as each item closes out. Category subtotals and the overall % complete card update automatically.
Overall % Complete |  |  |  | Complete |  | In Progress | Not Started
11.11% |  |  |  | 3 |  | 2 | 22
Category | Item / Task | Responsible Party | Status | Date Completed | Notes
Punch List | Final punch list walk completed with owner/architect | GC PE | Complete | 2026-07-22
Punch List | All punch list items signed off by responsible trade | GC Superintendent | In Progress
Punch List | Photo documentation of completed punch items | GC PE | Complete
Punch List | Outstanding punch items logged with completion dates | GC PE | Not Started
Punch List | Final punch list sign-off letter issued to owner | GC PM | Not Started
Punch List — Subtotal |  |  | 2/5 Complete
Warranty & O&M Documentation | O&M manuals collected from all subcontractors | GC PE | In Progress
Warranty & O&M Documentation | Warranty certificates collected and compiled | GC PE | Not Started
Warranty & O&M Documentation | As-built drawings finalized and submitted | Architect | Not Started
Warranty & O&M Documentation | Equipment startup/commissioning reports compiled | Commissioning Agent | Not Started
Warranty & O&M Documentation | Maintenance contact list provided to owner | GC PM | Not Started
Warranty & O&M Documentation — Subtotal |  |  | 0/5 Complete
Financial Closeout | All change orders reconciled and closed | GC PM | Complete | 2026-07-20
Financial Closeout | Final pay application submitted | GC PM | Not Started
Financial Closeout | Lien waivers collected from all subs/suppliers | GC PM | Not Started
Financial Closeout | Retainage release processed | Owner's Rep | Not Started
Financial Closeout | Final contract reconciliation completed | GC PM | Not Started
Financial Closeout — Subtotal |  |  | 1/5 Complete
Keys & Credential Handover | Master key set transferred to owner | GC Superintendent | Not Started
Keys & Credential Handover | Access control credentials/cards issued | Owner's Rep | Not Started
Keys & Credential Handover | Building automation system logins provided | Controls Sub | Not Started
Keys & Credential Handover | Security system codes documented and transferred | Security Sub | Not Started
Keys & Credential Handover — Subtotal |  |  | 0/4 Complete
Site & Common Areas | Final cleaning completed throughout | Cleaning Sub | Not Started
Site & Common Areas | Landscaping/irrigation final walkthrough | Landscape Sub | Not Started
Site & Common Areas | Signage installed and verified against approved package | Signage Sub | Not Started
Site & Common Areas | Temporary facilities/trailers removed from site | GC Superintendent | Not Started
Site & Common Areas — Subtotal |  |  | 0/4 Complete
Final Approvals & Occupancy | Certificate of Occupancy obtained | GC PM | Not Started
Final Approvals & Occupancy | Final fire marshal inspection passed | Fire Protection Engineer | Not Started
Final Approvals & Occupancy | AHJ final sign-off obtained | GC PM | Not Started
Final Approvals & Occupancy | Substantial completion certificate executed | Owner's Rep | Not Started
Final Approvals & Occupancy — Subtotal |  |  | 0/4 Complete

## README
Project Closeout Checklist — Template
Free field tool for PEs, Coordinators, and PMs — part of FieldToolsKit.com
WHAT THIS IS
A phase-gated closeout checklist covering the six areas that most commonly get left incomplete at substantial completion: punch list, warranty/O&M documentation, financial closeout, keys and credential handover, site restoration, and final approvals/occupancy.
DOES THIS REPLACE PROCORE'S PUNCH LIST / CLOSEOUT TOOLS?
No. If your firm has those modules active, use them as the system of record, this is meant to sit alongside them, not compete. It's built for firms without that software, and as a single-page way to see every category's status at once rather than navigating between modules.
HOW TO USE IT
1. Update Status for each item as it's completed: Not Started, In Progress, Complete, or N/A (for items that don't apply to this project type).
2. Fill in Date Completed and Notes as you go — these aren't required for the formulas to work, but they're what you'll want later if anyone asks when or how something closed out.
3. Add or remove rows for your project's specific requirements. This list is a strong starting point, not a universal standard — every project has a few closeout items unique to it.
HOW THE FORMULAS WORK
Each category has a subtotal row showing 'X of Y Complete' for that section, and an overall % Complete card at the top rolls up every item across all six categories. Both recalculate automatically as you update statuses — nothing here is a manual count.
COLOR KEY
Yellow fill = editable input cells.
Status: grey = not started, yellow = in progress, green = complete.
This is a free tool, not a substitute for your contract's actual closeout requirements or your jurisdiction's certificate-of-occupancy process. Confirm both before relying on this as your only closeout record.